## Grant Proposal Timeline
Rev. 06/07/2024 | GRANT PROPOSAL TIMELINE |  |  |  |  | 2024-05-27 | Memorial Day
ENTER SPONSOR DEADLINE HERE → |  |  |  |  | If Chapman is the primary applicant, enter the prime sponsor deadline here. If Chapman will be a subaward, enter the date that the prime applicant has requested Chapman's items be submitted. | 2024-06-19 | Juneteenth
Stage 1 Due by: | Stage 2 Due by: | Stage 3 Due by: | Stage 4 Due by: | Stage 5 Due by: |  | 2024-07-04 | Independence Day
#NUM! | #NUM! | #NUM! | #NUM! | #NUM! |  | 2024-07-05 | Extended Independence Day
(3-6 months) | (2 months) | (2-3 weeks) | (5 business days) | (2 business days) |  |  | NOTE: Holidays for AY24-25 and beyond are currently ESTIMATED as Chapman University's official holiday schedules have not yet been released.
Develop proposal idea and identify potential collaborators, if applicable. Discuss with Chair/Dean, if required by your college. | Start Cayuse SP proposal (this is your notification to SPS that you intend to apply). Provide link to the FOA so we can begin to review guidelines. | Route Cayuse SP proposal for internal approvals (requires drafts of the SOW, budget and budget justification). | Submit FULL DRAFT of application (including all required components) to SPS for review. | Submit FINAL application to SPS for submission to sponsor. |  | 2024-09-02 | Labor Day
Identify Funding Opportunity Announcement (FOA) and evaluate eligibility. COS Pivot is available to search for FOAs (https://pivot.proquest.com/funding_main) | If applicable, connect Grants Analyst or SPS Admin with subaward sites to request required docs (e.g., budgets and justifications, COI Disclosures, Subrecipient Commitment Forms) | No major changes to Chapman resources (e.g., PI effort, cost-share, etc.) should be made after routing in Cayuse SP. | You may continue to make minor edits to your documents beyond this date. SPS will not submit until PI provides approval of final proposal. | Proposals are submitted 2 business days before the sponsor deadline to allow time to address any unforeseen issues (technical problems, high proposal volume, etc.). |  | 2024-11-28 | Thanksgiving
Discuss project plan and proposal development responsibilities with collaborators (i.e., which team members are responsible for which parts of the proposal) . | Develop proposal budget with Grants Analyst or SPS Administrator. Schedule a meeting with Grants Analyst for proposal planning. | Grants Analyst to work with PI to finalize proposal package and upload administrative supplemental documents, as required by sponsor. | SPS to provide thorough evaluation of the proposal in comparison with sponsor and FOA guidelines (if appropriate time is given for review). | If necessary, identify and resolve submission errors. Resubmit application. |  | 2024-11-29 | Thanksgiving Friday
Confirm system registrations (e.g., eRA Commons, NSPIRES, etc.), if required by sponsor. | Submit required documents to collaborator sites for completion. Continue working with proposal team to develop project narrative. | Grants Analyst to work with PI to finalize budget and budget justification. SPS is available to assist/provide guidance. | SPS to provide PI and Grants Analyst with comments, issues, etc. found during proposal review. | After successful submission, SPS will provide confirmation to PI and/or Grants Analyst. |  | 2024-12-23 | Holiday Break
Submit letter of intent (LOI) if required by sponsor (route to SPS if institutional submission is needed). | Develop draft scope of work (SOW), draft Budget and Budget Justification for approvals routing. | PI and project team to complete development of project narrative and other science documents. | PI and Grants Analyst to address any concerns and finalize application. | Celebrate!!! |  | 2024-12-24 | Christmas Eve
[6 empty] | 2024-12-25 | Christmas Day
[6 empty] | 2024-12-26 | Holiday Break
[6 empty] | 2024-12-27 | Holiday Break
[6 empty] | 2024-12-30 | Holiday Break
[6 empty] | 2024-12-31 | New Year's Eve
[6 empty] | 2025-01-01 | New Year's Day
[6 empty] | 2025-01-20 | Martin Luther King Day
[6 empty] | 2025-03-28 | Cesar Chavez Day (observed)
[6 empty] | 2025-05-26 | Memorial Day
[6 empty] | 2025-06-19 | Juneteenth
[6 empty] | 2025-07-03 | Extended Independence Day
[6 empty] | 2025-07-04 | Independence Day
[6 empty] | 2025-09-01 | Labor Day
[6 empty] | 2025-11-27 | Thanksgiving
[6 empty] | 2025-11-28 | Thanksgiving Friday
[6 empty] | 2025-12-24 | Christmas Eve
[6 empty] | 2025-12-25 | Christmas Day
[6 empty] | 2025-12-26 | Holiday Break
[6 empty] | 2024-12-29 | Holiday Break
[6 empty] | 2025-12-30 | Holiday Break
[6 empty] | 2025-12-31 | New Year's Eve
[6 empty] | 2026-01-01 | New Year's Day
[6 empty] | 2026-01-02 | Holiday Break
[6 empty] | 2026-01-19 | Martin Luther King Day
[6 empty] | 2026-03-27 | Cesar Chavez Day (observed)
[6 empty] | 2026-05-25 | Memorial Day
[6 empty] | 2026-06-19 | Juneteenth
[6 empty] | 2026-07-03 | Independence Day (observed)
[6 empty] | 2026-07-06 | Extended Independence Day
[6 empty] | 2026-09-07 | Labor Day
[6 empty] | 2026-11-26 | Thanksgiving
[6 empty] | 2026-11-27 | Thanksgiving Friday
[6 empty] | 2026-12-24 | Christmas Eve
[6 empty] | 2026-12-25 | Christmas Day
[6 empty] | 2026-12-28 | Holiday Break
[6 empty] | 2026-12-29 | Holiday Break
[6 empty] | 2026-12-30 | Holiday Break
[6 empty] | 2026-12-31 | New Year's Eve
[6 empty] | 2027-01-01 | New Year's Day
[6 empty] | 2027-01-18 | Martin Luther King Day
[6 empty] | 2027-03-26 | Cesar Chavez Day (observed)
[6 empty] | 2027-05-31 | Memorial Day
[6 empty] | 2027-06-18 | Juneteenth
[6 empty] | 2027-07-02 | Independence Day (observed)
[6 empty] | 2027-07-05 | Extended Independence Day
[6 empty] | 2027-09-06 | Labor Day
[6 empty] | 2027-11-25 | Thanksgiving
[6 empty] | 2027-11-26 | Thanksgiving Friday
[6 empty] | 2027-12-23 | Holiday Break
[6 empty] | 2027-12-24 | Christmas Eve
Christmas Day (Saturday)
[6 empty] | 2027-12-27 | Holiday Break
[6 empty] | 2027-12-28 | Holiday Break
[6 empty] | 2027-12-29 | Holiday Break
[6 empty] | 2027-12-30 | Holiday Break
[6 empty] | 2027-12-31 | New Year's Eve
New Year's Day (Saturday)
[6 empty] | 2028-01-17 | Martin Luther King Day
[6 empty] | 2028-03-24 | Cesar Chavez Day (observed)
[6 empty] | 2028-05-29 | Memorial Day
[6 empty] | 2028-06-19 | Juneteenth
[6 empty] | 2028-07-03 | Extended Independence Day
[6 empty] | 2028-07-04 | Independence Day
[6 empty] | 2028-09-04 | Labor Day
[6 empty] | 2028-11-23 | Thanksgiving
[6 empty] | 2028-11-24 | Thanksgiving Friday
[6 empty] | 2028-12-22 | Holiday Break
[6 empty] | 2028-12-23 | Holiday Break
[6 empty] | 2028-12-24 | Christmas Eve
[6 empty] | 2028-12-25 | Christmas Day
[6 empty] | 2028-12-26 | Holiday Break
[6 empty] | 2028-12-27 | Holiday Break
[6 empty] | 2028-12-28 | Holiday Break
[6 empty] | 2028-12-29 | Holiday Break
New Year's Eve (Sunday)
[6 empty] | 2029-01-01 | New Year's Day
[6 empty] | 2029-01-15 | Martin Luther King Day
[6 empty] | 2029-03-23 | Cesar Chavez Day (observed)